## Dashboard
Manufacturing Execution System Project Phase: Proof of Concept
Engineering Project Action Tracker Dashboard ¦NCC - IPIC¦
The summary of PoC requirements, issues, and integration tasks.
| Status Summary |  | Priority Summary
| Open | 19 | Critical | 3
| NCC Closed | 7 | High | 15
| IPIC Closed | 0 | Medium | 8
|  |  | Low | 0

## Action Tracker
ID | Module / Area | Requirement / Action | Expected Outcome / Acceptance Criteria | Owner | Priority | Status | Target Date | Evidence / Reference | Closure Remarks
1 | Plant Live Views | Update Site Locations | All five sites correctly positioned on dashboard | IPIC | Medium | Open |  | Updated dashboard
2 | Downtime Command Center | Integrate Big Betti signals | Automatic event detection and timestamping from machine signals | IPIC | High | Open |  | I/O mapping / system demo
3 | Downtime Command Center | Configure operator downtime classification | Operator can assign appropriate downtime reason to detected events | IPIC | High | Open |  | System demonstration
4 | I/O Integration | Big Betti – ID 3 Run Mode | Signal logic correctly mapped to Run / Stop / Alarm conditions | NCC | High | NCC Closed | 2026-08-10 | I/O test / signal availability | Signal made available by NCC
5 | I/O Integration | Cartomac – ID 4 Run Mode | Signal correctly reflected in machine operating state | NCC | High | NCC Closed | 2026-08-10 | I/O test / signal availability | Signal made available by NCC
6 | I/O Integration | Euro-Pack Robot – ID 5 Run Mode | Steady / pulsing / OFF states correctly interpreted | NCC | High | NCC Closed | 2026-08-10 | I/O test / signal availability | Signal made available by NCC
7 | I/O Integration | Uni-Tech Wrapping Table – ID 5 | Table rotation available for Starved / Blocked detection | NCC | High | NCC Closed | 2026-08-10 | I/O test / signal availability | Signal made available by NCC
8 | I/O Integration | Uni-Tech Wrapping – ID 6 Run Mode | Run / Alarm / E-stop states correctly mapped | NCC | High | NCC Closed | 2026-08-10 | I/O test / signal availability | Signal made available by NCC
9 | OEE | Overall Line OEE methodology | Bottleneck Availability × Bottleneck Performance × Final Outfeed Quality | IPIC | Critical | Open |  | OEE calculation / report
10 | OEE | Starved state detection – Uni-Tech Wrapping | Downstream machine automatically changes to Starved when upstream product is unavailable | IPIC | Critical | Open |  | Live demonstration
11 | OEE | Blocked state detection – Uni-Tech Wrapping | Downstream constraint/accumulation correctly identified as Blocked | IPIC | High | Open |  | Live demonstration
12 | OEE | Starved/Blocked exclusion from OEE loss – Uni-Tech Wrapping | Starved/Blocked periods excluded according to agreed OEE calculation logic | IPIC | Critical | Open |  | OEE calculation validation
13 | Checkweigher | Relocate rejection sensor | Individual duplexes detected correctly without accumulated units being counted as one | NCC | High | NCC Closed | 2026-08-10 | Physical modification / production test | Sensor relocated by NCC to eliminate multiple-unit counting issue
14 | Euro-Pack Robot | Correct pallet counter sensor position | One sensor detection = one actual pallet | NCC | High | NCC Closed | 2026-08-10 | Physical modification / count validation | Sensor repositioned by NCC, previous 3× counting issue addressed
15 | Production KPI | Master Schedule Attainment | MSA KPI calculated and displayed correctly | IPIC | Medium | Open |  | KPI dashboard
16 | Production KPI | Volume-Based Capacity Utilization | Capacity Utilization KPI calculated against designed capacity | IPIC | Medium | Open |  | KPI dashboard
17 | Quality KPI | First Pass Yield | FPY calculation available and reflected in Quality Reports | IPIC | Medium | Open |  | Quality report
18 | Quality KPI | Defect Rate | Defect Rate calculated and reflected in Quality Reports | IPIC | Medium | Open |  | Quality report
19 | Maintenance KPI | MTBF calculation | Formula, downtime classification and inclusion/exclusion criteria documented | IPIC | High | Open |  | Calculation methodology
20 | Maintenance KPI | MTTR calculation | Formula, downtime classification and inclusion/exclusion criteria documented | IPIC | High | Open |  | Calculation methodology
21 | Maintenance KPI | MTBF/MTTR consistency | Maintenance Reports and Downtime Command Center produce consistent results | IPIC | High | Open |  | Cross-module validation
22 | Energy | Machine Energy Ratio | Energy ratio available at individual machine level | IPIC | Medium | Open |  | Energy dashboard
23 | Energy | WO Energy Ratio | Energy ratio linked to Work Order | IPIC | Medium | Open |  | WO / Energy report
24 | Energy / Sustainability | Scope 2 Carbon Footprint | kg CO₂e calculated from kWh × agreed grid emission factor | IPIC | Medium | Open |  | Energy dashboard
25 | Engineering Documentation | Production Line Instrumentation Layout | Machines, instruments, sensors, gateways and data acquisition points identified | IPIC | High | Open |  | Engineering drawing
26 | Engineering Documentation | Industrial Automation System Architecture | Complete automation pyramid showing machines, PLCs, field devices, networks, gateways, MES, etc. | IPIC | High | Open |  | Architecture drawing