## Summary
NCC PoC Enhancement Checklist – Summary
Metric | Value | Priority | Count
Total Actions | 29 | Critical | 8
Completed | 3 | High | 20
In Progress | 0 | Medium | 1
Blocked | 0
Under Review | 0 | Deadline Tracking | Value
Not Started | 26 | Deadlines Assigned | 0
Completion % | 10.34% | Overdue | 0
|  | Due in Next 7 Days | 0

## Action Checklist
NCC PoC Enhancement Action Checklist
ID | Module / Area | Requirement / Action Item | Acceptance Criteria | Priority | Status | Notes | Deadline | Responsible
1 | Plant Live Views – Line Dashboard | Update the 3D production line model to match the actual equipment configuration. | The model reflects the actual machines, sequence, position, orientation, conveyors, and production flow observed on site. | High | Not Started | Use the latest approved site layout and machine reference images.
2 | Plant Live Views – Line Dashboard | Update dashboard site locations using the latest coordinates shared by NCC. | All site/location markers display the latest approved coordinates and open the correct plant/location. | High | Not Started | Confirm the latest coordinate list before deployment.
3 | Downtime Command Center | Integrate the bottleneck machine stack-light signals with the downtime module. | The system receives and records the relevant stack-light state changes from the selected bottleneck machine. | Critical | Not Started | Confirm available signal colors, meanings, and communication method.
4 | Downtime Command Center | Automatically detect and timestamp production stops and resumptions. | Stop and restart events are created automatically with accurate start time, end time, and duration. | Critical | Not Started | Avoid duplicate events and define signal-debounce logic.
5 | Downtime Command Center | Limit operator input to classifying or assigning the downtime reason. | The system creates the event automatically; the operator only selects the reason/category and may add a comment. | High | Not Started | Keep a clear workflow for unclassified events.
6 | Downtime Command Center | Review planned and unplanned downtime classifications. | Each automatic or manual event is correctly classified as planned/unplanned and is used consistently in reports and OEE. | High | Not Started | Align classification rules across Downtime, OEE, and Maintenance modules.
7 | OEE – Overall Line Calculation | Verify the current method used to calculate overall line OEE. | A documented review confirms whether the current value is an average of machine OEEs or uses another method. | High | Not Started | Provide current calculation logic before applying changes.
8 | OEE – Overall Line Calculation | Implement bottleneck-based overall line OEE. | Overall Line OEE = Bottleneck Availability × Bottleneck Performance × Final Outfeed Quality. | Critical | Not Started | Big Betti is currently identified as the bottleneck for the PoC.
9 | OEE – Overall Line Calculation | Define and implement Final Outfeed Quality for the line. | The quality factor accounts for relevant downstream quality losses at the Checkweigher, Cartomac, Palletizer, and Wrapping Machine. | High | Not Started | Confirm how rejects and rework are captured at each stage.
10 | OEE – Machine-Level Logic | Automatically detect Starved conditions for downstream machines. | When product is unavailable from upstream, the machine state changes to Starved – External Loss instead of Running. | Critical | Not Started | Define the signal combination and minimum waiting duration.
11 | OEE – Machine-Level Logic | Automatically detect Blocked conditions where applicable. | When a machine cannot discharge because of a downstream constraint, its state changes to Blocked. | High | Not Started | Confirm that the required downstream/full-buffer signals are available.
12 | OEE – Machine-Level Logic | Exclude Starved and Blocked time from machine Availability and Performance losses. | External process constraints do not reduce the evaluated machine's Availability or Performance values. | Critical | Not Started | Document the exact inclusion/exclusion rules used in OEE calculations.
13 | OEE – PoC Demonstration | Demonstrate automated Starved/Blocked detection on the Palletizer or Wrapping Machine. | A working PoC demonstrates state detection using available stack-light signals and shows the effect on machine OEE. | Critical | Not Started | Select the machine with the most reliable and accessible signals.
14 | Analytics & Reports – Production KPIs | Add Master Schedule Attainment (MSA) to the dashboard. | The KPI is displayed with the agreed formula, scope, date range, target, actual value, and drill-down/source data. | High | Not Started | The formula was not visible in the received email; confirm it with NCC.
15 | Analytics & Reports – Production KPIs | Define the MSA calculation logic and required data sources. | A documented formula identifies the planned schedule, actual completed quantity/orders, cutoff rules, and exclusions. | High | Not Started | Confirm whether attainment is quantity-based, order-based, or schedule-line-based.
16 | Analytics & Reports – Production KPIs | Add Volume-Based Capacity Utilization to the dashboard. | The KPI compares actual production volume with the agreed available or rated capacity for the selected scope and period. | High | Not Started | The formula was not visible in the received email; confirm it with NCC.
17 | Analytics & Reports – Production KPIs | Define the Volume-Based Capacity Utilization calculation logic. | A documented formula identifies capacity basis, available hours, rated speed, planned shutdowns, and product mix rules. | High | Not Started | Confirm whether capacity is based on design, demonstrated, or planned capacity.
18 | Analytics & Reports – Quality KPIs | Correct First Pass Yield (FPY) values in Quality Reports. | FPY values calculated by the system appear correctly in the Quality Reports for the same scope and time period. | High | Not Started | Validate numerator, denominator, rework treatment, and report filters.
19 | Analytics & Reports – Quality KPIs | Correct Defect Rate values in Quality Reports. | Defect Rate values calculated by the system appear correctly in the Quality Reports for the same scope and time period. | High | Not Started | Confirm defect unit: units, cartons, batches, checks, or opportunities.
20 | Analytics & Reports – Maintenance | Document the MTBF calculation methodology used by the system. | The mathematical formula, equipment scope, period, failure definition, and included/excluded events are documented. | High | Not Started | Clarify whether planned downtime and external losses are excluded.
21 | Analytics & Reports – Maintenance | Document the MTTR calculation methodology used by the system. | The mathematical formula, repair start/end rules, equipment scope, period, and included/excluded events are documented. | High | Not Started | Clarify treatment of waiting for parts, approvals, and planned maintenance.
22 | Analytics & Reports – Maintenance | Define downtime classifications and event inclusion/exclusion rules for MTBF and MTTR. | A classification matrix shows which downtime reasons/events contribute to MTBF, MTTR, Availability, and reports. | High | Not Started | Use one consistent rule set across all modules.
23 | Analytics & Reports – Maintenance | Investigate and resolve the difference between Maintenance Reports and Downtime Command Center values. | The root cause is documented and both views show aligned values when the same scope, period, and filters are used. | Critical | Not Started | Check timezone, event status, filters, classifications, aggregation, and data source.
24 | Energy Module | Implement Energy Ratio KPIs by individual machine. | Energy consumption and the agreed energy ratio are available for each machine and selected time period. | High | Completed | Confirm the required ratio denominator, such as kWh/unit, kWh/carton, or kWh/kg.
25 | Energy Module | Implement Energy Ratio KPIs by Work Order. | Energy consumption and the agreed energy ratio are allocated and displayed for each work order. | High | Completed | Define allocation logic when several machines or work orders overlap.
26 | Energy Module | Add a Scope 2 GHG / Carbon Footprint KPI based on electricity consumption. | The dashboard calculates and displays Scope 2 emissions in kg CO2e for the selected scope and period. | High | Not Started | Formula: Total kWh consumed × Grid Emission Factor.
27 | Energy Module | Configure the KSA grid emission factor as 0.568 kg CO2e/kWh. | The factor is stored as a configurable value, applied to calculations, and displayed with its unit and effective source/date. | High | Not Started | Confirm with NCC whether 0.568 is fixed for the PoC or must be editable.
28 | Energy Module | Support relevant filters for Energy and Carbon KPIs. | KPIs can be filtered by machine, line, work order, and time period, subject to available metering data. | Medium | Completed | Confirm meter-to-machine mapping and data sampling interval.
29 | Technical Assessment & Delivery | Prepare the technical implementation approach for all requested enhancements. | A consolidated response identifies the solution, data/signals, dependencies, limitations, NCC inputs, priorities, and target dates. | Critical | Not Started | Required for review during the site visit and follow-up planning.

## Lists
Status | Priority
Not Started | Critical
In Progress | High
Blocked | Medium
Under Review
Completed